## Category
Type | Subject Category | Status
Information | Commercial | Open
Decision | Governance | In Progress
Action | Timeline | Closed
| Cadence | On Hold
| Configuration | Done
Implementation
Support
Enhancement
Bugs
Information
Updating the Data

## 12-1-26
Minutes of Meeting
|  | Topic : |  | Product Grooming: Feedback ADT & Weekly Plan
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-01-12 | From : | 13:30 | To : | 15:30
|  | Venue : |  | Sabang Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Okky Rizki Rohayat M. Fata | BUMA: Wahyu Kusdyantono Sunardi
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Information | Enhancement | Cancel Assignment of Inspection | Backlog improvement: Inspection - Ditambahkan fitur cancel assignment. | M. Fikhri A | 2026-01-05 | BTECH | - | In Progress | 1. Saat ini masih dalam proses testing di UAT enviroment 2. Nanti akan diassign ke supervisor dan superintendent
2 | Action | Configuration | Add Action Remedy to Inspection | Backlog improvement: Inspection - Menambahkan mapping action remedy pada bagian Component Detail untul all model equipment. 1. Top Up 2. Cleaning 3. Completed 4. Washing | 1. Suprapto 2. M Fikhri A | 2026-01-05 | BTECH | - | In Progress | Hanya update data configuration
3 | Action | Configuration | Add Component and Sub Component | Backlog improvement: Inspection - Menambahkan mapping "Frame & Chassis" pada bagian Component & Sub Component untuk model 6020B. | Suprapto | 2026-01-05 | BTECH | - | In Progress | Hanya update data configuration
4 | Action | Enhancement | Improvement on History (mobile) | Backlog improvement: Menampilkan referensi nomer Maintenance Order (MO) atas setiap orderan dari nomer e-MOL yang terbentuk di Digiman+. | Dea Marta W | 2026-01-05 | BTECH | - | Open | 1. Show Equipment Number 2. Show SAP MO Number that has been generated 3. View Details (P1: Inspection, Order, ada linkage) 4. Export to PDF (P1: inspection & order)
5 | Action | Enhancement | Auto create SAP MO MT03 & MT04 | Issue: Finding dan Order yang dibuat oleh user di Digiman+ yang masuk dalam kategori Maintenance Cost Type Undercarriage (MT03) dan Component (MT04), tidak muncul di SAP. Solusi: Digiman+ saat ini belum mengakomodir 2 type Maintenance Cost di atas, dikarenakan ada perlakuan khusus melihat umur component, historical order sebelumnya, penyediaan dokument support TIR dsb. | Suprapto | 2026-01-05 | BTECH | - | Open | 1. Cek di Dashboard apakah achievement Inspection and order terhitung. 2. Ada notification (email) ke user, beserta informasi data-data, foto, dll. (TIR: Technical Information Report). --> Planner,Planner CBM (melengkapi data), Planner PCR (orang yang membuat order). 3. Muncul pop notification ketika user milih MT03, MT04 bahwa MO tipe ini tidak akan terbentuk MO di SAP. --> Figma 4. Check email dari mas Wahyu
6 | Action | Enhancement | SAP Integration | Menambahkan informasi Model Unit, No. Unit, Hour Meter, Keterangan kerusakan, dan PIC Order dari output MO Digiman+ yang dikirim ke SAP pada Header Textnya. | Miftakhul Falah | 2026-01-05 | BTECH | - | Open | Sesuai contoh di excel
7 | Action | Enhancement | Multiple Section | Multiple Section |  |  | BTECH |  | Open | 1. Ada pilihan di homepage untuk memilih section --> assess terkait performance, ada warning ketika data local belum up to date 2. Authorization khusus 3. Assess impact terhadap cara penentuan section dari user yang sedang menggunakan apps
8 | Action | Bugs | SAP Integration failed | Sync SAP Failed partially |  |  | BTECH |  | Done
9 | Action | Bugs | MO Open empty | MO Backlog Execution tidak muncul list MO Open |  |  | BTECH |  | In Progress
10 | Action | Bugs | Score washing 0 | Input Washing Form, result score 0 |  |  | BTECH |  | In Progress
11 | Action | Enhancement | Download Response Enhancement | Score per area langsung score akhir (Download Form Response) dan juga score akhir |  |  | BTECH |  | Open
12 | Action | Enhancement | Workflow approval for Washing form | Approval Washing | Sunardi | 2026-01-12 | BTECH |  | Open | 1. Washing form perlu ada approval (2 level: Supervisor -> Superintendent) 2. Saat proses approval, user bisa edit data
13 | Action | Timeline | Effort and Timeline | Butuh detail effort and timeline sebelum menentukan mana yang lebih prioritas untuk dikerjakan | Wahyu K | 2026-01-12 | Okky |  | In Progress
14 | Information | Information | Service Sheet | Service sheet akan fokus untuk CBM terlebih dahulu | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open
15 | Action | Enhancement | Inspection Scheduler | Inspection Schedule should consider unit status | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open | 1. Unit status INPR saja yang perlu ada auto schedule 2. Integrasi unit status ke Digiman+
16

## 26-01-26
Minutes of Meeting
|  | Topic : |  | Product Grooming: Feedback ADT & Weekly Plan
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-01-26 | From : | 13:30 | To : | 15:30
|  | Venue : |  | Sabang Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Okky Rizki Rohayat M. Fata | BUMA: Sunardi
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Information | Enhancement | Cancel Assignment of Inspection | Backlog improvement: Inspection - Ditambahkan fitur cancel assignment. | M. Fikhri A | 2026-01-05 | BTECH | - | In Progress | 1. Saat ini masih dalam proses testing di UAT enviroment 2. Nanti akan diassign ke supervisor dan superintendent
2 | Action | Configuration | Add Action Remedy to Inspection | Backlog improvement: Inspection - Menambahkan mapping action remedy pada bagian Component Detail untul all model equipment. 1. Top Up 2. Cleaning 3. Completed 4. Washing | 1. Suprapto 2. M Fikhri A | 2026-01-05 | BTECH | - | In Progress | Hanya update data configuration
3 | Action | Configuration | Add Component and Sub Component | Backlog improvement: Inspection - Menambahkan mapping "Frame & Chassis" pada bagian Component & Sub Component untuk model 6020B. | Suprapto | 2026-01-05 | BTECH | - | In Progress | Hanya update data configuration
4 | Action | Enhancement | Improvement on History (mobile) | Backlog improvement: Menampilkan referensi nomer Maintenance Order (MO) atas setiap orderan dari nomer e-MOL yang terbentuk di Digiman+. | Dea Marta W | 2026-01-05 | BTECH | - | Open | 1. Show Equipment Number 2. Show SAP MO Number that has been generated 3. View Details (P1: Inspection, Order, ada linkage) 4. Export to PDF (P1: inspection & order)
5 | Action | Enhancement | Auto create SAP MO MT03 & MT04 | Issue: Finding dan Order yang dibuat oleh user di Digiman+ yang masuk dalam kategori Maintenance Cost Type Undercarriage (MT03) dan Component (MT04), tidak muncul di SAP. Solusi: Digiman+ saat ini belum mengakomodir 2 type Maintenance Cost di atas, dikarenakan ada perlakuan khusus melihat umur component, historical order sebelumnya, penyediaan dokument support TIR dsb. | Suprapto | 2026-01-05 | BTECH | - | Open | 1. Cek di Dashboard apakah achievement Inspection and order terhitung. 2. Ada notification (email) ke user, beserta informasi data-data, foto, dll. (TIR: Technical Information Report). --> Planner,Planner CBM (melengkapi data), Planner PCR (orang yang membuat order). 3. Muncul pop notification ketika user milih MT03, MT04 bahwa MO tipe ini tidak akan terbentuk MO di SAP. --> Figma 4. Check email dari mas Wahyu
6 | Action | Enhancement | SAP Integration | Menambahkan informasi Model Unit, No. Unit, Hour Meter, Keterangan kerusakan, dan PIC Order dari output MO Digiman+ yang dikirim ke SAP pada Header Textnya. | Miftakhul Falah | 2026-01-05 | BTECH | - | Open | Sesuai contoh di excel
7 | Action | Enhancement | Multiple Section | Multiple Section |  |  | BTECH |  | Open | 1. Ada pilihan di homepage untuk memilih section --> assess terkait performance, ada warning ketika data local belum up to date 2. Authorization khusus 3. Assess impact terhadap cara penentuan section dari user yang sedang menggunakan apps
8 | Action | Bugs | SAP Integration failed | Sync SAP Failed partially |  |  | BTECH |  | Done
9 | Action | Bugs | MO Open empty | MO Backlog Execution tidak muncul list MO Open |  |  | BTECH |  | Done | 3.0.6
10 | Action | Bugs | Score washing 0 | Input Washing Form, result score 0 |  |  | BTECH |  | Done | 3.0.6
11 | Action | Enhancement | Download Response Enhancement | Score per area langsung score akhir (Download Form Response) dan juga score akhir |  |  | BTECH |  | Open
12 | Action | Enhancement | Workflow approval for Washing form | Approval Washing | Sunardi | 2026-01-12 | BTECH |  | Open | 1. Washing form perlu ada approval (2 level: Supervisor -> Superintendent) 2. Saat proses approval, user bisa edit data
13 | Action | Timeline | Effort and Timeline | Butuh detail effort and timeline sebelum menentukan mana yang lebih prioritas untuk dikerjakan | Wahyu K | 2026-01-12 | Okky |  | Done
14 | Information | Information | Service Sheet | Service sheet akan fokus untuk CBM terlebih dahulu | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open
15 | Action | Enhancement | Inspection Scheduler | Inspection Schedule should consider unit status | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open | 1. Unit status INPR saja yang perlu ada auto schedule 2. Integrasi unit status ke Digiman+
16 | Information | Information | Approval E-MOL | Partial approval pada E-MOL, sebagian bisa dipending, sebagian bisa dilanjut | Sunardi | 2026-01-26 | BPO HO |  | Done
17 | Information | Information | Change EDD | Change EDD harus berkorelasi dengan priority | Sunardi | 2026-01-26 | BPO HO |  | Done
17 | Information | Information | Filter by Area in PM Shutdown | Mapping Equipment to Area akan dimaintain oleh orang site | Sunardi | 2026-01-26 | BPO HO |  | Done
18 | Action | Updating the Data | PM Shutdown Data | Data PM Shutdown dari 2025-Jul ke belakang di-Finish kan dan diberi notes, export data dulu untuk konfirmasi ke BPO semua data yang outstanding | Sunardi, Ekki | 2026-01-26 | BTECH |  | Open

## 09-02-26
Minutes of Meeting
|  | Topic : |  | Product Grooming: Feedback and Roadmap Prioritization
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-02-09 | From : | 13:30 | To : | 15:30
|  | Venue : |  | Sabang Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Okky Rizki Rohayat Soraya Faisal | BUMA: Wahyu K.
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Information | Enhancement | Cancel Assignment of Inspection | Backlog improvement: Inspection - Ditambahkan fitur cancel assignment. | M. Fikhri A | 2026-01-05 | BTECH | - | In Progress | 1. Saat ini masih dalam proses testing di UAT enviroment 2. Nanti akan diassign ke supervisor dan superintendent 3. Perlu enhance beberapa case belum dihandle dan akan release pada 3.1.0
2 | Action | Configuration | Add Action Remedy to Inspection | Backlog improvement: Inspection - Menambahkan mapping action remedy pada bagian Component Detail untul all model equipment. 1. Top Up 2. Cleaning 3. Completed 4. Washing | 1. Suprapto 2. M Fikhri A | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
3 | Action | Configuration | Add Component and Sub Component | Backlog improvement: Inspection - Menambahkan mapping "Frame & Chassis" pada bagian Component & Sub Component untuk model 6020B. | Suprapto | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
4 | Action | Enhancement | Improvement on History (mobile) | Backlog improvement: Menampilkan referensi nomer Maintenance Order (MO) atas setiap orderan dari nomer e-MOL yang terbentuk di Digiman+. | Dea Marta W | 2026-01-05 | BTECH | - | In Progress | 1. Show Equipment Number 2. Show SAP MO Number that has been generated 3. View Details (P1: Inspection, Order, ada linkage) 4. Export to PDF (P1: inspection & order)
5 | Action | Enhancement | Auto create SAP MO MT03 & MT04 | Issue: Finding dan Order yang dibuat oleh user di Digiman+ yang masuk dalam kategori Maintenance Cost Type Undercarriage (MT03) dan Component (MT04), tidak muncul di SAP. Solusi: Digiman+ saat ini belum mengakomodir 2 type Maintenance Cost di atas, dikarenakan ada perlakuan khusus melihat umur component, historical order sebelumnya, penyediaan dokument support TIR dsb. | Suprapto | 2026-01-05 | BTECH | - | Open | 1. Cek di Dashboard apakah achievement Inspection and order terhitung. 2. Ada notification (email) ke user, beserta informasi data-data, foto, dll. (TIR: Technical Information Report). --> Planner,Planner CBM (melengkapi data), Planner PCR (orang yang membuat order). 3. Muncul pop notification ketika user milih MT03, MT04 bahwa MO tipe ini tidak akan terbentuk MO di SAP. --> Figma 4. Check email dari mas Wahyu
6 | Action | Enhancement | SAP Integration | Menambahkan informasi Model Unit, No. Unit, Hour Meter, Keterangan kerusakan, dan PIC Order dari output MO Digiman+ yang dikirim ke SAP pada Header Textnya. | Miftakhul Falah | 2026-01-05 | BTECH | - | In Progress | Sesuai contoh di excel
7 | Action | Enhancement | Multiple Section | Multiple Section |  |  | BTECH |  | Open | 1. Ada pilihan di homepage untuk memilih section --> assess terkait performance, ada warning ketika data local belum up to date 2. Authorization khusus 3. Assess impact terhadap cara penentuan section dari user yang sedang menggunakan apps
8 | Action | Bugs | SAP Integration failed | Sync SAP Failed partially |  |  | BTECH |  | Done
9 | Action | Bugs | MO Open empty | MO Backlog Execution tidak muncul list MO Open |  |  | BTECH |  | Done | 3.0.6
10 | Action | Bugs | Score washing 0 | Input Washing Form, result score 0 |  |  | BTECH |  | Done | 3.0.6
11 | Action | Enhancement | Download Response Enhancement | Score per area langsung score akhir (Download Form Response) dan juga score akhir |  |  | BTECH |  | In Progress
12 | Action | Enhancement | Workflow approval for Washing form | Approval Washing | Sunardi | 2026-01-12 | BTECH |  | Open | 1. Washing form perlu ada approval (2 level: Supervisor -> Superintendent) 2. Saat proses approval, user bisa edit data
13 | Action | Timeline | Effort and Timeline | Butuh detail effort and timeline sebelum menentukan mana yang lebih prioritas untuk dikerjakan | Wahyu K | 2026-01-12 | Okky |  | Done
14 | Information | Information | Service Sheet | Service sheet akan fokus untuk CBM terlebih dahulu | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open
15 | Action | Enhancement | Inspection Scheduler | Inspection Schedule should consider unit status | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open | 1. Unit status INPR saja yang perlu ada auto schedule 2. Integrasi unit status ke Digiman+
16 | Information | Information | Approval E-MOL | Partial approval pada E-MOL, sebagian bisa dipending, sebagian bisa dilanjut | Sunardi | 2026-01-26 | BPO HO |  | Done
17 | Information | Information | Change EDD | Change EDD harus berkorelasi dengan priority | Sunardi | 2026-01-26 | BPO HO |  | Done
18 | Information | Information | Filter by Area in PM Shutdown | Mapping Equipment to Area akan dimaintain oleh orang site | Sunardi | 2026-01-26 | BPO HO |  | Done
19 | Action | Updating the Data | PM Shutdown Data | Data PM Shutdown dari 2025-Jul ke belakang di-Finish kan dan diberi notes, export data dulu untuk konfirmasi ke BPO semua data yang outstanding | Sunardi, Ekki | 2026-01-26 | BTECH |  | Done | Sudah dikirim sama Pak Indro
20 | Information | Information | On Progress Development | Saat ini tim sedang on progress development terkait feature gap Inspection Digiman+ terhadap Digiman lama, estimasi sementara release versi 3.1.0 adalah awal Maret 2026. | Okky | 2026-02-09 | BTECH |  | Done
21 | Information | Information | Product Implementation | Migrasi site IPR untuk fitur Inspection dari Digiman Lama ke Digiman+ dapat dilakukan setelah release 3.1.0 | Okky | 2026-02-09 | BTECH |  | Done
22 | Information | Information | Next Development | Setelah release 3.1.0, development akan fokus ke Feedback user terkait feature gap yang ada di Execution dan Breakdown Monitoring | Wahyu | 2026-02-09 | BPO HO |  | Open
23 | Action | Enhancement | Weekly Plan | Data relation antara weekly dan daily, bagaimana user membuat daily plan dari weekly plan, adhoc daily plan, carry over outstanding weekly plan to next weekly plan, visibility achievement per week | Wahyu, Okky | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
24 | Action | Enhancement | Execution | Pengawas ingin melihat isi dari MO backlog, ada berapa part untuk mencocokkan dengan part yang sudah disediakan saat service --> sudah ada di desain Figma sebelumnya | Wahyu | 2026-02-09 | BTECH |  | Open | Sudah ada di Figma, check
25 | Action | Enhancement | Weekly Plan | Weekly plan akan di Digiman+ web atau masih di platform lama | Okky, Wahyu | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
26 | Information | Enhancement | Service Sheet | Service sheet didahulukan dibanding weekly plan setelah tim menyelesaikan backlog terkait feature gap yang ada di Execution dan Breakdown Monitoring, weekly plan difinalkan dulu design di Figma-nya | Wahyu | 2026-02-09 | BPO HO |  | Done
27 | Action | Information | Feature Gap | Tambahkan semua feature gap Digiman+ dengan Digiman Lama ke sheet Timeline meskipun tidak critical | Wahyu | 2026-02-09 | BTECH |  | Done
28 | Action | Enhancement | Inspection Finding | User bisa input manhours / manpower saat membuat finding inspection | Wahyu | 2026-02-09 | BTECH |  | Open

## 09-03-2026
Minutes of Meeting
|  | Topic : |  | Product Grooming: Feedback and Roadmap Prioritization
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-03-09 | From : | 13:30 | To : | 15:30
|  | Venue : |  | Sabang Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Okky Rizki Rohayat Soraya Faisal | BUMA: Wahyu K.
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Information | Enhancement | Cancel Assignment of Inspection | Backlog improvement: Inspection - Ditambahkan fitur cancel assignment. | M. Fikhri A | 2026-01-05 | BTECH | - | In Progress | 1. Saat ini masih dalam proses testing di UAT enviroment 2. Nanti akan diassign ke supervisor dan superintendent 3. Perlu enhance beberapa case belum dihandle dan akan release pada 3.1.0
2 | Action | Configuration | Add Action Remedy to Inspection | Backlog improvement: Inspection - Menambahkan mapping action remedy pada bagian Component Detail untul all model equipment. 1. Top Up 2. Cleaning 3. Completed 4. Washing | 1. Suprapto 2. M Fikhri A | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
3 | Action | Configuration | Add Component and Sub Component | Backlog improvement: Inspection - Menambahkan mapping "Frame & Chassis" pada bagian Component & Sub Component untuk model 6020B. | Suprapto | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
4 | Action | Enhancement | Improvement on History (mobile) | Backlog improvement: Menampilkan referensi nomer Maintenance Order (MO) atas setiap orderan dari nomer e-MOL yang terbentuk di Digiman+. | Dea Marta W | 2026-01-05 | BTECH | - | In Progress | 1. Show Equipment Number 2. Show SAP MO Number that has been generated 3. View Details (P1: Inspection, Order, ada linkage) 4. Export to PDF (P1: inspection & order)
5 | Action | Enhancement | Auto create SAP MO MT03 & MT04 | Issue: Finding dan Order yang dibuat oleh user di Digiman+ yang masuk dalam kategori Maintenance Cost Type Undercarriage (MT03) dan Component (MT04), tidak muncul di SAP. Solusi: Digiman+ saat ini belum mengakomodir 2 type Maintenance Cost di atas, dikarenakan ada perlakuan khusus melihat umur component, historical order sebelumnya, penyediaan dokument support TIR dsb. | Suprapto | 2026-01-05 | BTECH | - | Open | 1. Cek di Dashboard apakah achievement Inspection and order terhitung. 2. Ada notification (email) ke user, beserta informasi data-data, foto, dll. (TIR: Technical Information Report). --> Planner,Planner CBM (melengkapi data), Planner PCR (orang yang membuat order). 3. Muncul pop notification ketika user milih MT03, MT04 bahwa MO tipe ini tidak akan terbentuk MO di SAP. --> Figma 4. Check email dari mas Wahyu
6 | Action | Enhancement | SAP Integration | Menambahkan informasi Model Unit, No. Unit, Hour Meter, Keterangan kerusakan, dan PIC Order dari output MO Digiman+ yang dikirim ke SAP pada Header Textnya. | Miftakhul Falah | 2026-01-05 | BTECH | - | In Progress | Sesuai contoh di excel
7 | Action | Enhancement | Multiple Section | Multiple Section |  |  | BTECH |  | Open | 1. Ada pilihan di homepage untuk memilih section --> assess terkait performance, ada warning ketika data local belum up to date 2. Authorization khusus 3. Assess impact terhadap cara penentuan section dari user yang sedang menggunakan apps
8 | Action | Bugs | SAP Integration failed | Sync SAP Failed partially |  |  | BTECH |  | Done
9 | Action | Bugs | MO Open empty | MO Backlog Execution tidak muncul list MO Open |  |  | BTECH |  | Done | 3.0.6
10 | Action | Bugs | Score washing 0 | Input Washing Form, result score 0 |  |  | BTECH |  | Done | 3.0.6
11 | Action | Enhancement | Download Response Enhancement | Score per area langsung score akhir (Download Form Response) dan juga score akhir |  |  | BTECH |  | In Progress
12 | Action | Enhancement | Workflow approval for Washing form | Approval Washing | Sunardi | 2026-01-12 | BTECH |  | Open | 1. Washing form perlu ada approval (2 level: Supervisor -> Superintendent) 2. Saat proses approval, user bisa edit data
13 | Action | Timeline | Effort and Timeline | Butuh detail effort and timeline sebelum menentukan mana yang lebih prioritas untuk dikerjakan | Wahyu K | 2026-01-12 | Okky |  | Done
14 | Information | Information | Service Sheet | Service sheet akan fokus untuk CBM terlebih dahulu | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open
15 | Action | Enhancement | Inspection Scheduler | Inspection Schedule should consider unit status | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Open | 1. Unit status INPR saja yang perlu ada auto schedule 2. Integrasi unit status ke Digiman+
16 | Information | Information | Approval E-MOL | Partial approval pada E-MOL, sebagian bisa dipending, sebagian bisa dilanjut | Sunardi | 2026-01-26 | BPO HO |  | Done
17 | Information | Information | Change EDD | Change EDD harus berkorelasi dengan priority | Sunardi | 2026-01-26 | BPO HO |  | Done
18 | Information | Information | Filter by Area in PM Shutdown | Mapping Equipment to Area akan dimaintain oleh orang site | Sunardi | 2026-01-26 | BPO HO |  | Done
19 | Action | Updating the Data | PM Shutdown Data | Data PM Shutdown dari 2025-Jul ke belakang di-Finish kan dan diberi notes, export data dulu untuk konfirmasi ke BPO semua data yang outstanding | Sunardi, Ekki | 2026-01-26 | BTECH |  | Done | Sudah dikirim sama Pak Indro
20 | Information | Information | On Progress Development | Saat ini tim sedang on progress development terkait feature gap Inspection Digiman+ terhadap Digiman lama, estimasi sementara release versi 3.1.0 adalah awal Maret 2026. | Okky | 2026-02-09 | BTECH |  | Done
21 | Information | Information | Product Implementation | Migrasi site IPR untuk fitur Inspection dari Digiman Lama ke Digiman+ dapat dilakukan setelah release 3.1.0 | Okky | 2026-02-09 | BTECH |  | Done
22 | Information | Information | Next Development | Setelah release 3.1.0, development akan fokus ke Feedback user terkait feature gap yang ada di Execution dan Breakdown Monitoring | Wahyu | 2026-02-09 | BPO HO |  | Open
23 | Action | Enhancement | Weekly Plan | Data relation antara weekly dan daily, bagaimana user membuat daily plan dari weekly plan, adhoc daily plan, carry over outstanding weekly plan to next weekly plan, visibility achievement per week | Wahyu, Okky | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
24 | Action | Enhancement | Execution | Pengawas ingin melihat isi dari MO backlog, ada berapa part untuk mencocokkan dengan part yang sudah disediakan saat service --> sudah ada di desain Figma sebelumnya | Wahyu | 2026-02-09 | BTECH |  | Open | Sudah ada di Figma, check
25 | Action | Enhancement | Weekly Plan | Weekly plan akan di Digiman+ web atau masih di platform lama | Okky, Wahyu | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
26 | Information | Enhancement | Service Sheet | Service sheet didahulukan dibanding weekly plan setelah tim menyelesaikan backlog terkait feature gap yang ada di Execution dan Breakdown Monitoring, weekly plan difinalkan dulu design di Figma-nya | Wahyu | 2026-02-09 | BPO HO |  | Done
27 | Action | Information | Feature Gap | Tambahkan semua feature gap Digiman+ dengan Digiman Lama ke sheet Timeline meskipun tidak critical | Wahyu | 2026-02-09 | BTECH |  | Done
28 | Action | Enhancement | Inspection Finding | User bisa input manhours / manpower saat membuat finding inspection | Wahyu | 2026-02-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Pada backlog execution hanya view materials saja tanpa select material yang diinstall | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Ketika centang backlog execution, muncul pop up pilihan take photo atau tidak a. Jika ya, open camera/select from gallery dan user take photo b. Jika tidak, backlog executed | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Detail materials yang ditampilkan: a. Order Qty dimunculkan b. Urutan Order Qty --> GI Qty, jika ada gap diberikan warning c. Storage location tidak perlu | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Action | Inspection & Execution | Backlog Execution | Exercise flow execute backlog: a. Take evidence apakah menjadi bagian dari flow b. Take evidence setelah backlog executed | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Improvement pada sync MO backlog untuk mendapatkan status GI lebih cepat. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Remark pada desain Figma Backlog Execution pindahin kedepan (level MO), pilihan sama dengan yang di Execution, namun beberapa pilihan di-hide yang tidak sesuai dengan inspection activity. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Information |  |  | Estimasi Release 2 akan dilakukan di Week 2 May 2026. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Done
29 | Information |  |  | Setelah Release 2, tim akan fokus melanjutkan journey product (Service Sheet & Weekly Plan). | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Done

## 13-04-2026
Minutes of Meeting
|  | Topic : |  | Product Grooming: Feedback and Roadmap Prioritization
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-04-13 | From : | 13:30 | To : | 14:30
|  | Venue : |  | Sabang Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Okky Rizki Rohayat Soraya Faisal Indro Adi N. Alimuddin Sodding Rizky DP Ekki MR Farizi | BUMA: Wahyu K. Sunardi M. Riza Pahlevi
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Information | Enhancement | Cancel Assignment of Inspection | Backlog improvement: Inspection - Ditambahkan fitur cancel assignment. | M. Fikhri A | 2026-01-05 | BTECH | - | Done | 3.1.0 on 19 Mar 2026
2 | Action | Configuration | Add Action Remedy to Inspection | Backlog improvement: Inspection - Menambahkan mapping action remedy pada bagian Component Detail untul all model equipment. 1. Top Up 2. Cleaning 3. Completed 4. Washing | 1. Suprapto 2. M Fikhri A | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
3 | Action | Configuration | Add Component and Sub Component | Backlog improvement: Inspection - Menambahkan mapping "Frame & Chassis" pada bagian Component & Sub Component untuk model 6020B. | Suprapto | 2026-01-05 | BTECH | - | Done | Hanya update data configuration Released in 3.0.7
4 | Action | Enhancement | Improvement on History (mobile) | Backlog improvement: Menampilkan referensi nomer Maintenance Order (MO) atas setiap orderan dari nomer e-MOL yang terbentuk di Digiman+. | Dea Marta W | 2026-01-05 | BTECH | - | Done | 3.1.0 on 19 Mar 2026
5 | Action | Enhancement | Auto create SAP MO MT03 & MT04 | Issue: Finding dan Order yang dibuat oleh user di Digiman+ yang masuk dalam kategori Maintenance Cost Type Undercarriage (MT03) dan Component (MT04), tidak muncul di SAP. Solusi: Digiman+ saat ini belum mengakomodir 2 type Maintenance Cost di atas, dikarenakan ada perlakuan khusus melihat umur component, historical order sebelumnya, penyediaan dokument support TIR dsb. | Suprapto | 2026-01-05 | BTECH | - | Done | 1. Cek di Dashboard apakah achievement Inspection and order terhitung. 2. Ada notification (email) ke user, beserta informasi data-data, foto, dll. (TIR: Technical Information Report). --> Planner,Planner CBM (melengkapi data), Planner PCR (orang yang membuat order). 3. Muncul pop notification ketika user milih MT03, MT04 bahwa MO tipe ini tidak akan terbentuk MO di SAP. --> Figma 4. Check email dari mas Wahyu 5. Tidak dapat diakomodir di sisi product karena tidak sesuai product journey, Digiman+ seharusnya bisa membuat MO apapun ke SAP, yang membatasi bisa tidaknya adalah sistem dari client sendiri
6 | Action | Enhancement | SAP Integration | Menambahkan informasi Model Unit, No. Unit, Hour Meter, Keterangan kerusakan, dan PIC Order dari output MO Digiman+ yang dikirim ke SAP pada Header Textnya. | Miftakhul Falah | 2026-01-05 | BTECH | - | Done | 3.1.0 on 19 Mar 2026
7 | Action | Enhancement | Multiple Section | Multiple Section |  |  | BTECH |  | Open | 1. Ada pilihan di homepage untuk memilih section --> assess terkait performance, ada warning ketika data local belum up to date 2. Authorization khusus 3. Assess impact terhadap cara penentuan section dari user yang sedang menggunakan apps
8 | Action | Bugs | SAP Integration failed | Sync SAP Failed partially |  |  | BTECH |  | Done
9 | Action | Bugs | MO Open empty | MO Backlog Execution tidak muncul list MO Open |  |  | BTECH |  | Done | 3.0.6
10 | Action | Bugs | Score washing 0 | Input Washing Form, result score 0 |  |  | BTECH |  | Done | 3.0.6
11 | Action | Enhancement | Download Response Enhancement | Score per area langsung score akhir (Download Form Response) dan juga score akhir |  |  | BTECH |  | Done | 3.1.0 on 19 Mar 2026
12 | Action | Enhancement | Workflow approval for Washing form | Approval Washing | Sunardi | 2026-01-12 | BTECH |  | Open | 1. Washing form perlu ada approval (2 level: Supervisor -> Superintendent) 2. Saat proses approval, user bisa edit data
13 | Action | Timeline | Effort and Timeline | Butuh detail effort and timeline sebelum menentukan mana yang lebih prioritas untuk dikerjakan | Wahyu K | 2026-01-12 | Okky |  | Done
14 | Information | Information | Service Sheet | Service sheet akan fokus untuk CBM terlebih dahulu | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Closed
15 | Action | Enhancement | Inspection Scheduler | Inspection Schedule should consider unit status | Wahyu K, Sunardi | 2026-01-12 | BPO HO |  | Done | 1. Unit status INPR saja yang perlu ada auto schedule 2. Integrasi unit status ke Digiman+
16 | Information | Information | Approval E-MOL | Partial approval pada E-MOL, sebagian bisa dipending, sebagian bisa dilanjut | Sunardi | 2026-01-26 | BPO HO |  | Done
17 | Information | Information | Change EDD | Change EDD harus berkorelasi dengan priority | Sunardi | 2026-01-26 | BPO HO |  | Done
18 | Information | Information | Filter by Area in PM Shutdown | Mapping Equipment to Area akan dimaintain oleh orang site | Sunardi | 2026-01-26 | BPO HO |  | Done
19 | Action | Updating the Data | PM Shutdown Data | Data PM Shutdown dari 2025-Jul ke belakang di-Finish kan dan diberi notes, export data dulu untuk konfirmasi ke BPO semua data yang outstanding | Sunardi, Ekki | 2026-01-26 | BTECH |  | Done | Sudah dikirim sama Pak Indro
20 | Information | Information | On Progress Development | Saat ini tim sedang on progress development terkait feature gap Inspection Digiman+ terhadap Digiman lama, estimasi sementara release versi 3.1.0 adalah awal Maret 2026. | Okky | 2026-02-09 | BTECH |  | Done
21 | Information | Information | Product Implementation | Migrasi site IPR untuk fitur Inspection dari Digiman Lama ke Digiman+ dapat dilakukan setelah release 3.1.0 | Okky | 2026-02-09 | BTECH |  | Done
22 | Information | Information | Next Development | Setelah release 3.1.0, development akan fokus ke Feedback user terkait feature gap yang ada di Execution dan Breakdown Monitoring | Wahyu | 2026-02-09 | BPO HO |  | Done
23 | Action | Enhancement | Weekly Plan | Data relation antara weekly dan daily, bagaimana user membuat daily plan dari weekly plan, adhoc daily plan, carry over outstanding weekly plan to next weekly plan, visibility achievement per week | Wahyu, Okky | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
24 | Action | Enhancement | Execution | Pengawas ingin melihat isi dari MO backlog, ada berapa part untuk mencocokkan dengan part yang sudah disediakan saat service --> sudah ada di desain Figma sebelumnya | Wahyu | 2026-02-09 | BTECH |  | Open | Sudah ada di Figma, check
25 | Action | Enhancement | Weekly Plan | Weekly plan akan di Digiman+ web atau masih di platform lama | Okky, Wahyu | 2026-02-09 | BTECH |  | Open | Perlu diasses lebih lanjut
26 | Information | Enhancement | Service Sheet | Service sheet didahulukan dibanding weekly plan setelah tim menyelesaikan backlog terkait feature gap yang ada di Execution dan Breakdown Monitoring, weekly plan difinalkan dulu design di Figma-nya | Wahyu | 2026-02-09 | BPO HO |  | Done
27 | Action | Information | Feature Gap | Tambahkan semua feature gap Digiman+ dengan Digiman Lama ke sheet Timeline meskipun tidak critical | Wahyu | 2026-02-09 | BTECH |  | Done
28 | Action | Enhancement | Inspection Finding | User bisa input manhours / manpower saat membuat finding inspection | Wahyu | 2026-02-09 | BTECH |  | Open
29 | Decision | Inspection & Execution | Backlog Execution | Pada backlog execution hanya view materials saja tanpa select material yang diinstall | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Closed | As per the current design, select material will be default as all selected
30 | Decision | Inspection & Execution | Backlog Execution | Ketika centang backlog execution, muncul pop up pilihan take photo atau tidak a. Jika ya, open camera/select from gallery dan user take photo b. Jika tidak, backlog executed | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Closed | As per the current design, we should minimize animations so it won’t be too heavy.
31 | Decision | Inspection & Execution | Backlog Execution | Detail materials yang ditampilkan: a. Order Qty dimunculkan b. Urutan Order Qty --> GI Qty, jika ada gap diberikan warning c. Storage location tidak perlu | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
32 | Action | Inspection & Execution | Backlog Execution | Exercise flow execute backlog: a. Take evidence apakah menjadi bagian dari flow b. Take evidence setelah backlog executed | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Closed | Digiman+ will be more general, where evidence of material installment will be not mandatory
33 | Decision | Inspection & Execution | Backlog Execution | Improvement pada sync MO backlog untuk mendapatkan status GI lebih cepat. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
33 | Decision | Inspection & Execution | Backlog Execution | Remark pada desain Figma Backlog Execution pindahin kedepan (level MO), pilihan sama dengan yang di Execution, namun beberapa pilihan di-hide yang tidak sesuai dengan inspection activity. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Open
29 | Information |  |  | Estimasi Release 2 akan dilakukan di Week 2 May 2026. | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Done
29 | Information |  |  | Setelah Release 2, tim akan fokus melanjutkan journey product (Service Sheet & Weekly Plan). | Sunardi, Indro, Okky, Soraya | 2026-03-09 | BTECH |  | Done
33 | Decision | Digiman Dashboard | Digiman Transaction | Data man hours estimated untuk setiap finding dimunculin di raw data di dashboard | Wahyu | 2026-04-13 | BTECH |  | Open
33 | Decision | Digiplan | Auto create unscheduled plan | Auto create planning unschedule tidak perlu menunggu 30 menit dari start breakdown notif | Sunardi | 2026-04-13 | BTECH |  | Open
33
33

## Release 4.0.0
No backlog grooming during release 4.0.0 preaparation
|  |  | 9:00 |  | 11:30
Bromo Room, BTECH Office, Tower A, South Quarter Level 2
| BTECH: Alimudin Sodding Okky RR Faisal P Indro AN Robert Laila | BUMA: Sunardi Anas
Sunardi
Sunardi
Sunardi
Sunardi
|  | Sunardi |  | BUMA
Sunardi
| PSCS memiliki alur approval: Submit oleh Mechanic, kemudian approve oleh Supervisor, Planner, dan Superintendent. | Sunardi
Sunardi
Sunardi
Sunardi
Sunardi
Sunardi
Sunardi

## 11-06-2026
Minutes of Meeting
|  | Topic : |  | Backlog Grooming Service Sheet
|  | Project Name : |  | Digiman+ Product Roadmap 2026
|  | Date : |  | 2026-06-11 | From : | 9:00 | To : | 11:30
|  | Venue : |  | Bromo Room, BTECH Office, Tower A, South Quarter Level 2
|  | Attendees : |  | BTECH: Alimudin Sodding Okky RR Faisal P Indro AN Robert Laila | BUMA: Sunardi Anas
Meeting Summary
No. | Type | Subject Category | Subject | Description | Raised by | Raised Date | PIC | Due Date | Status | Remarks
1 | Decision | Product Development | Priority of Product Journey | Yang menjadi prioritas development adalah service sheet (PSCS), baru kemudian form approval, dan Equipment Area. | Sunardi | 2026-06-11 | BUMA, BTECH | - | Closed
2 | Decision | Form & UI | Form Tab Consolidation | Beberapa form akan digabungkan menjadi satu dalam bentuk tab. | Sunardi | 2026-06-11 | BTECH | - | Open
3 | Decision | Form & UI | Progress Indicator (DONE) | Diharapkan terdapat indikator progress DONE all task pada setiap tab. | Sunardi | 2026-06-11 | BTECH | - | Open
4 | Decision | Form & UI | Color Scheme Selection | Perlu diperhatikan pemilihan warna — sebisa mungkin hindari warna-warna soft/pastel, karena kondisi pencahayaan di lapangan sangat terang/silau. | Sunardi | 2026-06-11 | BTECH | - | Open
5 | Decision | Mechanic Flow & User Management | Mechanic Self-Service Form Input | Mechanic akan mengisi form secara mandiri (kemungkinan hanya ditampilkan list mechanic, lalu mechanic dapat bertindak sebagai dirinya sendiri). | Sunardi | 2026-06-11 | BTECH | - | Open
6 | Action | Mechanic Flow & User Management | General Account Setup | Perlu disiapkan account general, termasuk konfigurasinya. | Sunardi | 2026-06-11 | BUMA | - | Open
7 | Decision | Mechanic Flow & User Management | Mechanic Activity Detail Logging | Aktivitas mechanic perlu dicatat secara detail, ada start and end. | Sunardi | 2026-06-11 | BTECH | - | Open
8 | Decision | PSCS Approval & EMOL | PSCS Approval Flow | PSCS memiliki alur approval: Submit oleh Mechanic, kemudian approve oleh Supervisor, Planner, dan Superintendent. | Sunardi | 2026-06-11 | BTECH | - | Open
9 | Decision | PSCS Approval & EMOL | PSCS Approval Dependency on EMOL | Approval PSCS baru dapat dilakukan setelah EMOL dibuat (created). | Sunardi | 2026-06-11 | BTECH | - | Open
10 | Decision | PSCS Approval & EMOL | EMOL Creation Authorization | Pembuatan EMOL dapat dilakukan oleh Inspector atau assigned user. | Sunardi | 2026-06-11 | BTECH | - | Open
11 | Decision | Reference & Scope | Development Focus: Hauler & Loader | Fokus pengembangan form saat ini pada unit Hauler dan Loader. | Sunardi | 2026-06-11 | BTECH | - | Open
12 | Action | Action Items | Create Flow Process | BTECH membuat Flow Process sesuai hasil diskusi pada meeting ini. | Sunardi | 2026-06-11 | BTECH | - | Open
13 | Action | Action Items | Share Bank Task Template | BTECH membagikan template untuk bank task dan panduan tipe task. | Sunardi | 2026-06-11 | BTECH | - | Open
14 | Action | Action Items | Create Progress Timeline | BPO request dibuatkan progress timeline, dengan fokus PSCS sampai integrasi dengan EHMS, serta opsi tambahan untuk inspection form. | Sunardi | 2026-06-11 | BTECH | - | Open

## Timeline
EPIC | Feature | Product Backlog | Feature Gap | Category | Priority | Effort | Est. Story Point | Release | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6 |  |  |  | Month 7 |  |  |  | Month 8 |  |  |  | Month 9 |  |  |  | Month 10 |  |  |  | Month 11 |  |  |  | Month 12
[9 empty] | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Inspection | Assign to | Cancel Assignment | Yes | Feedback | P1 | High |  | 1
SAP Integration | Order to SAP Order | Modify MO description to include Model Unit, No. Unit, Hour Meter, Damage, and PIC Order |  | Feedback | P1 | Medium |  | 1
History | Transaction history list | Add some informations (unit number, etc) on transaction history list |  | Feedback | P1 | High |  | 1
History | View History Details | User can view transaction history details |  | Enhancement |  | High |  | 1
History | Export to PDF | User can export to PDF for each transaction history where submitted by themselves (specifically for Inspection) | Yes | Feedback | P1 | High |  | 1
Form | Download Response | Specific for washing form: show the final score per area and all area. |  | Feedback | P1 | Medium |  | 1
Order | Pop Up warning for MT03 & MT04 | Show warning message when user select MT03 or MT04 |  | Feedback | P3 | Low
Order | Email Notification | Send email notification for planner regarding order information of MT03 or MT04 |  | Feedback | P2 | Medium
Inspection | Inspection Scheduler | Inspection Schedule should consider unit status |  | Feedback | P1 | High |  | 2
General Feature | Multiple section | Authorized user can change to other section via homepage |  | Feedback | P2 | High
General Feature | Multiple section | Handling master data synchronization after user change section |  | Feedback | P2 | High
General Feature | Multiple section | Apply multiple section on Inspection |  | Feedback | P2 | High
General Feature | Multiple section | Apply multiple section on Order |  | Feedback | P2 | High
General Feature | Multiple section | Apply multiple section on PM Shutdown |  | Feedback | P2 | High
General Feature | Multiple section | Apply multiple section on Form |  | Feedback | P2 | High
Inspection | Autocreate Inspection | Additional Inspection now affects the next scheduled inspection creation, do we need to change? |  | Enhancement |  | Low
Inspection | Offline Mode Improvement | Sync inspection data by comparing dates to handle inspections that have become Closed by system |  | Enhancement |  | High
Inspection | Autocreate Inspection | Additional Inspection now affects the next manual uploaded inspection, do we need to change? |  | Enhancement |  | Low
General Feature | Offline Mode Improvement | Improvement on how to sync get data master and transaction |  | Enhancement |  | High
General Feature | Offline Mode Improvement | Improve offline sync monitoring page to be more user friendly |  | Enhancement |  | High
Form | Offline Mode Improvement | Form submission should record sync time data |  | Enhancement |  | Medium
Inspection | Findings | Multi-user's finding visibility |  | Feedback | P2 | High
Inspection | Supervisor Intervention | Supervisors can intervent the outstanding inspection from their team |  | Feedback | P2 | High
Inspection | Supervisor Intervention | Partial approval of E-MOL |  | Feedback | P2 | High
Order | Edit EDD | User can edit EDD when creating EMOL |  | Feedback | P2 | Medium
General Feature | Homepage | Homepage Revamp |  | Enhancement |  | High
General Feature | Menus | Form menus revamp |  | Enhancement |  | High
General Feature | Menus | Inspection, PM Shutdown, Corrective Breakdown menus and page revamp |  | Enhancement |  | High
Execution | Work | Setelah edit search tidak langsung berubah datanya sesuai yg diinput pada field search, user harus klik button search terlebih dahulu |  | Feedback | P3 | Medium
Execution | Work | Menambahkan field filter area (source data ambil dari BPS via API (main equipment), selain itu perlu dibuatkan mekanisme upload) |  | Feedback | P1 | Medium
Execution | Work | "…" bagian shotcut terdapat menu add work in progress & delay |  | Feedback | P2 | Medium
Execution | Work | "…" bagian shortcut terdapat menu untuk input atau edit "Estimasi RFU" |  | Feedback | P2 | Medium
Execution | Work | Task yang tidak di eksekusi harus mengisi remark terlebih dahulu sebelum melakukan finish execution, dan bisa multiple remark serta untuk yg status task dengan MOnya "Waiting Supply" bisa langsung otomatis |  | Feedback | P1 | Medium |  | 2
Execution | Information Delay | Copy paste laporan on progress dan delay |  | Feedback | P3 | Medium
Breakdown Monitoring | Unscheduled | Description "New Task 1" pada template "Unscheduled" breakdown langsung terisi sesuai deskripsi breakdown pada notifikasi |  | Feedback | P1 | Medium |  | 2
Breakdown Execution | Breakdown Task (Gantchart) | Tambahkan fitur "Import from Excel" pada halaman breakdown execution saat statusnya "In Progress" |  | Feedback | P3 | High
Execution | Work | Penambahan action "PIN" atau "FAVORITE" pada halaman monitoring breakdown "WORK" untuk mempermudah user dalam focus terhadap unit-unit yang sedang diperbaiki. |  | Feedback | P3 | High
Planning | Start Execution | Scheduled service seharusnya sudah termapping dengan notif-nya, sehingga tidak perlu lagi user manual start namun bisa langsung otomatis berdasarkan data breakdown yang diupdate oleh dispatcher |  | Feedback | P2 | High
Planning | Weekly Plan | Ketika user melakukan create planning baru maka data planning sebelumnya yang masih outstanding bisa langsung "auto cancel planning" --> masuk ke roadmap weekly plan |  | Feedback |  | Medium
Breakdown Monitoring | Unscheduled | Plan duration terhadap breakdown unscheduled seharusnya 0 Hrs --> related to Description "New Task 1" |  | Feedback | P1 | Low |  | 2
General Feature | Site assigment | Applikasi tidak dapat menghandel jika ada pekerja (pengawas) dari site lain |  | Feedback | P3 | High
Breakdown Monitoring | Breakdown Monitoring | Quantity breakdown saat masih in progress beda antara BPS dan Digiman+ |  | Feedback | P1 | Medium |  | 2
WICOPE Check | WICOPE Check | Form WICOPE Check dibatasi per unit |  | Feedback | P2 | High
Breakdown Monitoring / Execution | Breakdown Monitoring / Execution | PIC shutdown bisa lebih dari satu karena pekerjaan bisa lanjut di shift berikutnya |  | Feedback | P2 | Medium
Execution | Execution | Pengawas ingin melihat isi dari MO backlog, ada berapa part untuk mencocokkan dengan part yang sudah disediakan saat service |  | Feedback | P2 | Medium
Execution | Execution | Pengawas ingin melihat history pekerjaan yang sudah dilakukan, part apa yang terpasang/ganti |  | Feedback | P2 | High
Breakdown Monitoring/Historical | Breakdown Monitoring/Historical | Ada informasi histori berapa kali estimasi RFU diubah |  | Feedback | P2 | High
Breakdown Monitoring / Execution | Historical | Filter equipment tidak auto search |  | Feedback | P3 | Medium
Breakdown Monitoring | Breakdown Monitoring | Improve Breakdown Monitoring to consider notification status, breakdown without notif, etc |  | Feedback | P1 | High |  | 2
Execution | Execution | Outstanding administration transaction mechanism |  | Feedback | P1 | High |  | 2
Planning | Weekly Plan | Hide button Summary Plan pada page Weekly Planning |  | Roadmap |  | Low
Planning | Weekly Plan | Review PS/Shutdown Backlog - Informasi Submission Progress pada Data Weekly Planning |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Add feature 'Execution Confirm' per MO (shortcut) in tab MO Backlog |  | Roadmap |  | Medium
Planning | Weekly Plan | Monitoring Service - Rename Label “Select” to “Filter” |  | Roadmap |  | Low
Planning | Weekly Plan | Perubahan naming Sub-Menu Weekly Planning dan Daily Planning |  | Roadmap |  | Low
Planning | Weekly Plan | Review PS/Shutdown Backlog - Behavior value ETA supply, logic 'Execution Confirm' dan format date upload excel |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Create Daily Planning |  | Roadmap |  | High
Planning | Weekly Plan | Monitoring Service - Adjustment Create Weekly Planning |  | Roadmap |  | High
Planning | Weekly Plan | Review PS/Shutdown Backlog - Alignment & Styling Button |  | Roadmap |  | Low
Planning | Weekly Plan | Review PS/Shutdown Backlog - Enhancement perhitungan Duration pada pop-up edit MO |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Behavior & Default Logic Execution Confirm berdasarkan Kondisi Material dan ETA Supply pada MO |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Add feature for Multiple 'Execution Confirm' in Tab MO Backlog |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Penyesuai validasi & tampilan upload excel pada tampilan Preview Upload |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Penyesuaian naming file download & upload |  | Roadmap |  | Low
Planning | Weekly Plan | Review PS/Shutdown Backlog - Download data yang mengandung data error pada feature Upload Data |  | Roadmap |  | Low
Planning | Weekly Plan | Review PS/Shutdown Backlog - Feature select for Approve data |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Enhancement tampilan grouping material order per MO Child pada tab MO Backlog |  | Roadmap |  | Medium
Planning | Weekly Plan | Review PS/Shutdown Backlog - Penyesuaian tampilan pop-up action edit pada tab MO Backlog |  | Roadmap |  | Medium
Planning | Weekly Plan | Enhancement behavior status weekly planning dan label status |  | Roadmap |  | High
Form | Form Integration Configuration | Create a configuration to integrate form to other features |  | Roadmap |  | Medium
Form | CBM Configuration | CBM threshold configuration list |  | Roadmap |  | Medium
Form | CBM Configuration | Add/Edit CBM threshold configuration |  | Roadmap |  | High
Form | CBM Configuration | Upload CBM Threshold configuration |  | Roadmap |  | High
Form | CBM Configuration | Export CBM Threshold to Excel |  | Roadmap |  | Medium
Form | Service Sheet | Service Sheet for CBM task |  | Roadmap |  | Medium
Form | Service Sheet | Integrate Service Sheet to PM Shutdown |  | Roadmap |  | High
Form | Service Sheet | Integrate Service Sheet to external system (provide API) |  | Roadmap |  | High
Form | Form Workflow | Integrate to Approval Workflow (especially Washing Form) |  | Feedback | P2 | High
Form | Inspection Form | Integrate Form to Inspection |  | Enhancement |  | High
Form | Inspection Form | Integrate Inspection Form to external system (provide API) |  | Enhancement |  | High
Form | Export form to PDF | Export form to PDF |  | Roadmap |  | Medium
Form | Service Sheet Renderer | Make form renderer on mobile to render complex form |  | Roadmap
Planning | Weekly Plan | Projection PA |  | Roadmap |  | High
Planning | Weekly Plan | Projection RM Cost |  | Roadmap |  | High
Notification | Notification | In-App Notification Engine |  | Enhancement |  | High
Notification | Notification | Email Notification Engine |  | Enhancement |  | High
Notification | Notification | Implement Notification to Inspection |  | Enhancement |  | High
Notification | Notification | Implement Notification to Execution |  | Enhancement |  | High
Notification | Notification | Implement Notification to Order |  | Enhancement |  | High
Notification | Notification | Implement Notificatin to Form |  | Enhancement |  | High
My Work | My Assignment | Integrate to Inspection |  | Roadmap |  | High
My Work | My Assignment | Integrate to Order |  | Roadmap |  | High
My Work | My Assignment | Integrate to Execution (PM Shutdown) |  | Roadmap |  | High
My Work | My Assignment | Integrate to Form |  | Roadmap |  | High
My Work | My Assignment | Additional Assignment |  | Roadmap |  | High
My Work | Input Activities (Non Technical Task) | View My Activities (Time Table) |  | Roadmap |  | High
My Work | Input Activities (Non Technical Task) | View My Team Activities (Time Table) |  | Roadmap |  | High
My Work | Input Activities (Non Technical Task) | Add Activities |  | Roadmap |  | High
My Work | Input Activities (Non Technical Task) | Edit Activities |  | Roadmap |  | High
My Work | Input Activities (Non Technical Task) | View my activity history |  | Roadmap |  | High
My Work | My Approval Task | Integrate Workflow Task to My Work for SPV above |  | Roadmap
E-MAR | E-MAR Data Source | Populate E-MAR Data Source from PM Shutdown |  | Roadmap |  | High
E-MAR | E-MAR Data Source | Populate E-MAR Data Source from Inspection |  | Roadmap |  | High
E-MAR | E-MAR Data Source | Populate E-MAR Data Source from Order |  | Roadmap |  | High
E-MAR | E-MAR Data Source | Populate E-MAR Data Source from Form |  | Roadmap |  | High
E-MAR | E-MAR Data Source | Populate E-MAR Data Source from Activities (Non technical) |  | Roadmap |  | High
E-MAR | E-MAR Submission | View my today's E-MAR |  | Roadmap |  | High
E-MAR | E-MAR Submission | Submit my today's E-MAR |  | Roadmap |  | High
E-MAR | E-MAR Submission | Integrate E-MAR to Workflow |  | Roadmap |  | High
E-MAR | E-MAR Submission | Integrate to SAP |  | Roadmap |  | High
E-MAR | E-MAR Submission | Integrate to People Card |  | Roadmap |  | High
E-MAR | E-MAR Dashboard | Data ingestion |  | Roadmap |  | High
E-MAR | E-MAR Dashboard | Create Dashboard (Web version) |  | Roadmap |  | High
E-MAR | E-MAR Dashboard | Create simple dashboard for mobile |  | Roadmap |  | High
E-MAR | E-MAR History | View my E-MAR History |  | Roadmap |  | High
Order | Web Order | Web order - Part book catalogue | Yes | Enhancement |  | Medium
Order | Web Order | Web order - Bulk material upload | Yes | Enhancement |  | High
Order | Web Order | Monitoring order | Yes | Enhancement |  | High
Mobile Dashboard | Simple Dashboard | Dashboard R&M Cost & pareto issue | Yes | Enhancement |  | High
Order | Mobile Order | Mobile - Part book catalogue | Yes | Enhancement |  | Medium
Order | Mobile Order | Mobile - Bulk material upload | Yes | Enhancement |  | High
Inspection | Inspection Finding | User bisa input manhours atau required man power saat membuat finding inspection |  | Feedback |  | Medium
Execution | Execution - Mobile | Pengawas ingin melihat isi dari MO backlog, ada berapa part untuk mencocokkan dengan part yang sudah disediakan saat service |  | Feedback | P2 | High |  | 2